## WBS
Gantt Chart - Aquila Health Network Analytics Project
Task No | Task Name | Duration | Predecessors | Resource Names
0 | Aquila Health Network - Business Analytics Dashboard
1 | Requirements Definition
2 | Kickoff & Scope Alignment | 3 days | 1 | Karen Lin
3 | Stakeholder Requirements Gathering | 5 days | 2 | Karen Lin
4 | Business KPI Definition | 4 days | 2 | Karen Lin
5 | Functional Requirements Specification (FRS) | 5 days | 3,4 | Karen Lin
6 | Sponsor Review & FRS Approval | 2 days | 5 | Karen Lin, Dan Stone
7 | Data Architecture & Modeling
8 | Logical Data Model Design (ERD) | 7 days | 1 | Karen Lin
9 | Physical Schema Design | 5 days | 8 | Karen Lin
10 | Synthetic Data Requirements Specification | 3 days | 9 | Karen Lin
11 | Synthetic Dataset Generation | 5 days | 10 | Karen Lin
12 | Data Quality Review & Validation | 3 days | 11 | Karen Lin
13 | Analytics Dashboard Development
14 | Power BI Data Mart Build | 4 days | 7 | Karen Lin
15 | Executive Summary Dashboard | 4 days | 14 | Karen Lin
16 | Appointment & No-Show Dashboard | 4 days | 15 | Karen Lin
17 | Provider Utilization Dashboard | 3 days | 16 | Karen Lin
18 | Referral Performance Dashboard | 3 days | 17 | Karen Lin
19 | Patient Access Wait Time Dashboard | 3 days | 18 | Karen Lin
20 | Dashboard Testing & Refinement | 3 days | 15,16,17,18,19 | Karen Lin, Dan Stone
21 | Predictive Analytics (Proof of Concept)
22 | No-Show Risk Model Design | 3 days | 13 | Karen Lin
23 | Model Development & Training | 5 days | 22 | Karen Lin
24 | Model Validation & Performance Review | 3 days | 23 | Karen Lin
25 | Power BI Predictive Integration | 3 days | 24 | Karen Lin
26 | Analysis, Documentation & Delivery
27 | Findings Synthesis & Business Impact Analysis | 3 days | 21 | Karen Lin
28 | Final Project Report | 4 days | 27 | Karen Lin
29 | Client-Facing Presentation Deck | 3 days | 27 | Karen Lin
30 | Final Sponsor Review | 1 day | 28,29 | Karen Lin, Dan Stone
31 | Project Submission | 1 day | 30 | Karen Lin